## Behandlet logg
Operational Lookahead for A & B template wells
|  | Start of Project | 02.07.2023 10:00 | [11 empty] | Updated 24.07.23
|  |  |  | Brønn 1 | Time estimated |  | Estimate | Actual | ahead- /behind+ | Cumulative |  | NOW |  |  | 28.09.2023 13:48
Well |  | Phase | Start Time | Operation Description | Clean time | Time (D10) | Time | Time | From Best operational time (D10) Days | Days | Finish Time | WOW (Hrs) | NPT (Hrs) | Scope in | Comments | Gjeldende operasjonell grenseverdi
Brønn 1 | Prepare well for PCE deployment | 20 | 23:45 man 03 jul | Perform DP Trials and handover well from Field. | 2 | 2.08 | 2 | 2 | -1.47 | 1.66 | 01:45 tir 04 jul |  |  |  |  | Subsea support/IMR (Hs= 4,0 m)
Brønn 1 |  | 25 | 01:45 tir 04 jul | Deploy ROV, Deploy ROV baskets, Carry out "As Found" Survey & place transponders. Open well protection structure hatches on Brønn 1 & Brønn 2. | 6 | 6.24 | 6 | 4.5 | -1.54 | 1.84 | 06:15 tir 04 jul |  |  |  | Opened structure hatches on Brønn2 & Brønn3. | Subsea support/IMR (Hs= 4,0 m)
Brønn 1 |  | 30 | 06:15 tir 04 jul | Remove TDC and carried out acid treatment. | 3 | 3.12 | 3 | 11.5 | -1.2 | 2.32 | 17:45 tir 04 jul |  | 6.75 |  | Repaired Guidewire # 1 prior to skidding in WCP. ROV preparation on Brønn 2 | Subsea support/IMR (Hs= 4,0 m)
Brønn 1 | Install PCE | 35 | 17:45 tir 04 jul | Skid in WCP, Install VX seal gasket and establish GW`s. | 3 | 3.12 | 3 | 3.5 | -1.18 | 2.47 | 21:15 tir 04 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 40 | 21:15 tir 04 jul | Deploy WCP, land WCP, lock connector, retrieve WCP RT | 7 | 7.28 | 7 | 6 | -1.23 | 2.72 | 03:15 ons 05 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 45 | 03:15 ons 05 jul | Establis GW`s, Deploy LS, lock LLP/WCP connector, install jumpers (El. & Hyd.flying leads), unlock RT, retrieve LS RT, perform pressure testing of WCP and LS. | 8 | 8.32 | 6 | 5 | -1.37 | 2.93 | 08:15 ons 05 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 1 | THCP operation | 50 | 08:15 ons 05 jul | RU PCH, MU UTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 3 | -1.38 | 3.05 | 11:15 ons 05 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 55 | 11:15 ons 05 jul | Release from TC, RIH, land and retreive UTHCP, POOH into TC, retrieve UTHCP BHA, LD BHA. | 5 | 5.2 | 5.2 | 4.5 | -1.41 | 3.24 | 15:45 ons 05 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 60 | 15:45 ons 05 jul | RU PCH, MU LTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 2.5 | -1.43 | 3.34 | 18:15 ons 05 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 65 | 18:15 ons 05 jul | Release from TC, RIH, land and retreive LTHCP, POOH into TC, retrieve LTHCP BHA, LD BHA. | 6 | 6.24 | 6.24 | 5.75 | -1.45 | 3.58 | 00:00 tor 06 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Well circulation | 70 | 00:00 tor 06 jul | Rig up 1 x Well Service hose and HC vent hose, attach to WCP. | 4 | 4.16 | 4.16 | 4 | -1.46 | 3.75 | 04:00 tor 06 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Drift run | 75 | 04:00 tor 06 jul | RU PCH, MU BHA for Drift run, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 2 | -1.51 | 3.83 | 06:00 tor 06 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 80 | 06:00 tor 06 jul | Release from TC. RIH to tailpipe below production packer, POOH into TC. | 7 | 7.28 | 7.28 | 9.75 | -1.4 | 4.24 | 15:45 tor 06 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 85 | 15:45 tor 06 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 4.25 | -1.36 | 4.42 | 20:00 tor 06 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Combined IPDT with setting lower deep set bridge plug | 145 | 20:00 tor 06 jul | Line up Well Service hose towards well and dispace/ bullhead well with 2 ea well tubing volume. | 0 | 0 | 2.6 | 3.5 | -2.75 | 4.56 | 23:30 tor 06 jul |  |  |  | Tubing volume 60 x 2= 120 m3 Annulus volume 181 x 3= 543 m3 Added: Combined IPDT and lower deep set bridge plug. | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 150 | 23:30 tor 06 jul | RU PCH & BHA for Tubing Puncher on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 4 | -2.58 | 4.73 | 03:30 fre 07 jul |  |  |  | Added: Combined IPDT and lower deep set bridge plug. | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 155 | 03:30 fre 07 jul | Release from TC, RIH, Correlate, adjust Delta P TBG/Annulus, activate Puncher and punch TBG, POOH 50 m | 0 | 0 | 5.2 | 12.5 | -2.06 | 5.25 | 16:00 fre 07 jul |  |  |  | Added: Combined IPDT and lower deep set bridge plug. | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 160 | 16:00 fre 07 jul | Line up Well service hose towards annulus and displaced / bullhead annulus with treated sea water or simular and displace well with 3ea annulus volume xx m³ into reservoir. | 0 | 0 | 3.12 | 8 | -1.73 | 5.58 | 00:00 lør 08 jul |  |  |  | Tubing volume 60 x 2= 120 m3 Annulus volume 181 x 3= 543 m3 Added: Combined IPDT and lower deep set bridge plug | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 165 | 00:00 lør 08 jul | Release IPDT and RIH to Lower Deep set bridge plug area, correlate, set deepset bridge plug. POOH into TC | 0 | 0 | 5.2 | 4 | -1.56 | 5.75 | 04:00 lør 08 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 175 | 04:00 lør 08 jul | LP/HP and inflow test the lower deep set bridge plug | 0 | 0 | 4.16 | 13.25 | -1.01 | 6.3 | 17:15 lør 08 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Upper Deep Barrier plug operation | 145 | 17:15 lør 08 jul | RU PCH, MU BHA for Upper Deep -set Bridge / Barrier plug on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 2.25 | -1.04 | 6.4 | 19:30 lør 08 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 150 | 19:30 lør 08 jul | WOW, HC vent less than 4,5 knot | 0 | 0 | 0 | 4.5 | -0.86 | 6.58 | 00:00 søn 09 jul | 4.5 |  |  | HC vent less than 4,5 knot | Wire Line Intervention (Hs= 6,0 m) + Min wind speed = 6 knot
Brønn 1 |  | 155 | 00:00 søn 09 jul | Performed inflow test on lower deep set bridge plug , unable to test plug | 0 | 0 | 0 | 2 | -0.77 | 6.67 | 02:00 søn 09 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 160 | 02:00 søn 09 jul | Dsicussed way forward, performed second inflow test, test failed , decided to RIH with planned upper deep set bridge plug | 0 | 0 | 0 | 7.25 | -0.47 | 6.97 | 09:15 søn 09 jul |  |  | 7.25 | Start NPT failed test on lower deep set bridge plug 09.07-02:00 - 14.7 -03:30 = 121,5 hrs includig 18,5 NPT on stroker failure | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 150 | 09:15 søn 09 jul | Release from TC, RIH to TD, correlate, set Upper Deep set Bridge, line up and perform LP/ HP leak test, POOH into TC. | 10 | 10.4 | 10.4 | 11 | -0.45 | 7.43 | 20:15 søn 09 jul |  |  | 11 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 155 | 20:15 søn 09 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 3.25 | -0.44 | 7.56 | 23:30 søn 09 jul |  |  | 3.25 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Third deep set bridge plug | 160 | 23:30 søn 09 jul | RU PCH, MU BHA for Upper Deep -set Bridge / Barrier plug on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 4 | -0.27 | 7.73 | 03:30 man 10 jul |  |  | 4 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 165 | 03:30 man 10 jul | Release from TC, RIH to TD, correlate, set Upper Deep set Bridge / Barrier # 3 Above packer tail pipe at 5014m mMD, line up and perform LP/ HP leak test, POOH into TC. | 0 | 0 | 10 | 8 | 0.06 | 8.06 | 11:30 man 10 jul |  |  | 8 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 170 | 11:30 man 10 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 3 | 3.5 | 0.21 | 8.21 | 15:00 man 10 jul |  |  | 3.5 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Retrieval of Bridge plug # 3 | 175 | 15:00 man 10 jul | RU PCH, MU BHA for retrieval of plug # 3 with stroker /GS on e line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 5 | 0.41 | 8.42 | 20:00 man 10 jul |  |  | 5 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 180 | 20:00 man 10 jul | Release from TC, RIH to TD, above plug, activate stroker and POOH into TC with plug | 0 | 0 | 7 | 7 | 0.71 | 8.71 | 03:00 tir 11 jul |  |  | 7 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 185 | 03:00 tir 11 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 3.12 | 3 | 0.83 | 8.83 | 06:00 tir 11 jul |  |  | 3 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Retrieval of Bridge plug # 2 | 190 | 06:00 tir 11 jul | RU PCH, MU BHA for retrieval of plug # 2 with stroker /GS on e line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 4 | 1 | 9 | 10:00 tir 11 jul |  |  | 4 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 195 | 10:00 tir 11 jul | Release from TC, RIH to TD, above plug, activate stroker and POOH into TC with plug | 0 | 0 | 7 | 8 | 1.33 | 9.33 | 18:00 tir 11 jul |  |  | 8 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 200 | 18:00 tir 11 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 3.12 | 3.75 | 1.49 | 9.49 | 21:45 tir 11 jul |  |  | 3.75 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Attempted to pull BP #1 | 205 | 21:45 tir 11 jul | RU PCH, MU BHA for retrieval of plug 1 with stroker /GS on e line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 3.5 | 1.63 | 9.64 | 01:15 ons 12 jul |  |  | 3.5 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 210 | 01:15 ons 12 jul | Release from TC, RIH to TD, above plug, activate stroker release plug, Unable to activate anchor on stroker. | 0 | 0 | 7 | 4 | 1.8 | 9.8 | 05:15 ons 12 jul |  |  | 4 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 215 | 05:15 ons 12 jul | Activated RSS and release stroker from BHA, POOH and layed down BHA | 0 | 0 | 0 | 12.5 | 2.32 | 10.32 | 17:45 ons 12 jul |  |  | 12.5 | NPT on stroker failure | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Retrieval of Bridge plug # 1 | 205 | 17:45 ons 12 jul | RU PCH, MU new BHA for retrieval of fish/plug # 1 with stroker /GS on e line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 2.75 | 2.43 | 10.44 | 20:30 ons 12 jul |  |  | 2.75 | NPT on stroker failure | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 210 | 20:30 ons 12 jul | Release from TC, RIH to TD, above plug, activate stroker release plug. | 0 | 0 | 7 | 3.25 | 2.57 | 10.57 | 23:45 ons 12 jul |  |  | 3.25 | NPT on stroker failure | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 215 | 23:45 ons 12 jul | Release plug & POOH into TC with plug. | 0 | 0 | 0 | 3.75 | 2.73 | 10.73 | 03:30 tor 13 jul |  |  | 3.75 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 215 | 03:30 tor 13 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 3.12 | 6.5 | 3 | 11 | 10:00 tor 13 jul |  |  | 6.5 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Installing bridge plug in blank pipe section in the swellpacker @ 5246 mMD | 220 | 10:00 tor 13 jul | RU PCH, MU BHA 400-550 HPHT plug for Barrier plug on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 2.75 | 3.11 | 11.11 | 12:45 tor 13 jul |  |  | 2.75 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 225 | 12:45 tor 13 jul | Release from TC, RIH to TD, correlate, set Bridge / Barrier blank pipe section at 5246 m mMD, line up and perform LP/ HP leak test, POOH into TC. | 0 | 0 | 8 | 8 | 3.44 | 11.45 | 20:45 tor 13 jul |  |  | 8 | Possitive test on 400-500 HPHT plug | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 230 | 20:45 tor 13 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. Prepare BHA Upper deep set bridge plug on deck | 0 | 0 | 3.12 | 6.75 | 3.73 | 11.73 | 03:30 fre 14 jul |  |  | 6.75 | Failed barrier testing, primary barrier | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Installing bridge plug in blank pipe section above the glass plug | 235 | 03:30 fre 14 jul | RU PCH, MU BHA 440 - 700 THEX HPHT plug for Barrier plug on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 2.25 | 3.82 | 11.82 | 05:45 fre 14 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 240 | 05:45 fre 14 jul | Lost communication with 440 - 700 THEX electronic setting tool (EST), fault finding and made up new cablehead on EST | 0 | 0 | 0 | 10.25 | 4.25 | 12.25 | 16:00 fre 14 jul |  | 10.25 |  | Lost comms with BHA during barrier testing. Recovered toolstring to surface and troubleshot. Found issue with setting tool and changed out. | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 240 | 16:00 fre 14 jul | Release from TC, RIH to TD, correlate, set Bridge / Barrier blank pipe section at 5246 m mMD, line up and perform LP/ HP leak test, POOH into TC. | 0 | 0 | 8 | 11.25 | 4.72 | 12.72 | 03:15 lør 15 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 245 | 03:15 lør 15 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 3.12 | 7.5 | 5.03 | 13.03 | 10:45 lør 15 jul |  |  |  | Cut cable & reterminate cable head | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Tubing cutting | 160 | 10:45 lør 15 jul | RU PCH, MU BHA for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 3.25 | 5.03 | 13.17 | 14:00 lør 15 jul |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 1 |  | 165 | 14:00 lør 15 jul | Release from TC, RIH to TBG section just above Production Packer , correlate and cut tubing @ 5003 mMD, POOH into TC. | 9 | 9.36 | 9.36 | 7 | 4.94 | 13.46 | 21:00 lør 15 jul |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 1 |  | 170 | 21:00 lør 15 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 3 | 4.93 | 13.58 | 00:00 søn 16 jul |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 1 | Barrier plug operation | 175 | 00:00 søn 16 jul | RU PCH, MU BHA for Shallow-set Bridge plug plug with IBV & stinger , deploy BHA/PCH and perform well entry pressure test. | 3.5 | 3.64 | 3.64 | 4.5 | 4.97 | 13.77 | 04:30 søn 16 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 |  | 180 | 04:30 søn 16 jul | Release from TC. RIH and install shallow set Bridge plug across TRSSSV area allow to keep TRSSSV flapper open , POOH and LD BHA. Perform LP/HP leak test of plug. | 7 | 7.28 | 7.28 | 4.5 | 4.85 | 13.96 | 09:00 søn 16 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Well circulation | 185 | 09:00 søn 16 jul | Retrieve Well Service and HC vent hose. | 2 | 2.08 | 2.08 | 2.5 | 4.87 | 14.06 | 11:30 søn 16 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 1 | Retriveve PCE | 190 | 11:30 søn 16 jul | Recover Lubricator section. | 6 | 6.24 | 6.24 | 5.75 | 4.85 | 14.3 | 17:15 søn 16 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 195 | 17:15 søn 16 jul | Change out LS pump. Test and rack back. | 0 | 0 | 3 | 13.75 | 5.42 | 14.88 | 07:00 man 17 jul |  | 13.75 |  | NPT for troubleshoot and repair of moonpool acess basket. | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 200 | 07:00 man 17 jul | Skidded WCP RT to MP, open hatches, Lifted WCP oif Brønn 1 | 0 | 0 | 3 | 5.75 | 5.66 | 15.11 | 12:45 man 17 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 200 | 12:45 man 17 jul | Retrieve WCP to deck and secure in park position. Change out & test the XT controller pump on WCP. | 0 | 0 | 5 | 15.25 | 6.3 | 15.75 | 04:00 tir 18 jul |  | 15.25 |  | Change Pumps on XT controller | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 205 | 04:00 tir 18 jul | Barrier testing of WCP. | 0 | 0 | 8 | 5 | 6.5 | 15.96 | 09:00 tir 18 jul |  |  |  | BOP testing | Umbilical – max disconnect (Hs= 7,0 m)
Brønn 1 |  | 210 | 09:00 tir 18 jul | Continued with in between well testing due to eHPU pump change out | 0 | 0 | 11 | 11.25 | 6.97 | 16.43 | 20:15 tir 18 jul |  | 11.25 |  | Change Pumps on XT controller | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 210 | 20:15 tir 18 jul | WOW prior to deploy WCP | 0 | 0 | 16 | 5.5 | 7.2 | 16.66 | 01:45 ons 19 jul |  | 5.5 |  | Change Pumps on XT controller | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 215 | 01:45 ons 19 jul | Prepared to Deploy WCP, worked on escaping trapped air in Connector | 0 | 0 | 4 | 4.25 | 7.38 | 16.83 | 06:00 ons 19 jul |  | 4.25 |  | Change Pumps on XT controller | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 215 | 06:00 ons 19 jul | Worked on Guide post issue on Brønn 2 , | 0 | 0 | 3 | 6.5 | 7.65 | 17.1 | 12:30 ons 19 jul |  | 6.5 |  | Guides Posts | Module deployment (Hs= 4,0 m)
Brønn 1 |  | 230 | 12:30 ons 19 jul | Deployed WCP RT to top of Brønn 2 | 0 | 0 | 0 | 1.5 | 7.24 | 17.17 | 14:00 ons 19 jul |  | 1.5 |  | Change Pumps on XT controller | Module deployment (Hs= 4,0 m)
|  |  |  | Repeate the operation on Brønn 2. | [7 empty] | 0.19 | 3.13 | 5.06 | days
|  |  |  | Sum days D10 Actual, End of operation Brønn 1 | 10.04 | 10.32 | 17.39 | 17.17 |  |  |  | 0.01 | 0.18 | 0.29 | %
12.55 4.61
|  |  |  | Brønn 2 | Time estimated |  | CWIS estimate | Actual | ahead- /behind+ | Cumulative
|  | Phase | Start Time | Operation Description | Clean time | Time (D10) | Time | Time | From Best operational time (D10) | Days | Finish Time | WOW (Hrs) | NPT (Hrs) | Scope in | Comments | Gjeldende operasjonell grenseverdi
Brønn 2 | Install PCE | 5 | 14:00 ons 19 jul | Landed WCP on Brønn 2, retrieved WCP RT, Establis GW`s, Deploy LS, lock LLP/WCP connector, install jumpers (El. & Hyd. flying leads), unlock RT, retrieve LS RT, perform pressure testing of WCP and LS. | 8 | 8.32 | 8.32 | 10 | 0.08 | 17.58 | 00:00 tor 20 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 2 |  | 6 | 00:00 tor 20 jul | GL # 4 Not back in operation | 0 | 0 | 0 | 0.5 | 0.1 | 17.6 | 00:30 tor 20 jul |  |  |  | GL # 4 Not back in operation | Module deployment (Hs= 4,0 m)
Brønn 2 | THCP operation | 10 | 00:30 tor 20 jul | RU PCH, MU UTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 2.75 | 0.09 | 17.72 | 03:15 tor 20 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 15 | 03:15 tor 20 jul | Release from TC, RIH, land and retreive UTHCP, POOH into TC, retrieve UTHCP BHA, LD BHA. | 5 | 5.2 | 5.2 | 4.25 | 0.05 | 17.9 | 07:30 tor 20 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 20 | 07:30 tor 20 jul | RU PCH, MU LTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 1.5 | -0.02 | 17.96 | 09:00 tor 20 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 25 | 09:00 tor 20 jul | Release from TC, RIH, land and retreive LTHCP, POOH into TC, retrieve LTHCP BHA, LD BHA. | 6 | 6.24 | 6.24 | 5.75 | -0.04 | 18.2 | 14:45 tor 20 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 | Well circulation | 30 | 14:45 tor 20 jul | Rig up 1 x Well Service hose and HC vent hose, attach to WCP. | 4 | 4.16 | 4.16 | 4.25 | -0.04 | 18.38 | 19:00 tor 20 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 | Drift run | 35 | 19:00 tor 20 jul | RU PCH, MU BHA for xx" Drift run, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 3.25 | -0.03 | 18.51 | 22:15 tor 20 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 40 | 22:15 tor 20 jul | Release from TC. RIH to tailpipe below production packer, POOH into TC. | 7 | 7.28 | 7.28 | 6.5 | -0.06 | 18.78 | 04:45 fre 21 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 45 | 04:45 fre 21 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 4.25 | -0.02 | 18.96 | 09:00 fre 21 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 | Combined IPDT with setting lower deep set bridge plug | 105 | 09:00 fre 21 jul | Line up towards Annulus and pressure test annulus to 200 bar, bleed off, MU BHA # 4 while prepare for bullheading tubing | 0 | 0 | 3 | 13.25 | -1 | 19.51 | 22:15 fre 21 jul | 5.25 |  |  | WoW due to less than 5 knot wind | Wire Line Intervention (Hs= 6,0 m) + Min wind speed = 6 knot
Brønn 2 |  | 105 | 22:15 fre 21 jul | Line up Well Service hose towards well and dispace/ bullhead well with 2 ea well tubing volume. | 0 | 0 | 2.6 | 2 | -0.92 | 19.59 | 00:15 lør 22 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 115 | 00:15 lør 22 jul | Release from TC, RIH, Correlate, adjust Delta P TBG/Annulus, activate Puncher and punch TBG, POOH 50 m | 0 | 0 | 5.2 | 11.75 | -0.43 | 20.08 | 12:00 lør 22 jul |  |  |  | Experienced Stick & slip | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 120 | 12:00 lør 22 jul | Line up Well service hose towards annulus and displaced / bullhead annulus with treated sea water or simular and displace well with 2ea annulus volume xx m³ into reservoir. | 0 | 0 | 3.12 | 2.5 | -0.32 | 20.19 | 14:30 lør 22 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 125 | 14:30 lør 22 jul | Release IPDT and RIH to Lower Deep set bridge plug area, correlate, set deepset bridge plug. POOH into TC | 0 | 0 | 5.2 | 1 | -0.28 | 20.23 | 15:30 lør 22 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 130 | 15:30 lør 22 jul | POOH into TC. Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 2.06 | 4.5 | -0.09 | 20.42 | 20:00 lør 22 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 135 | 20:00 lør 22 jul | LP/HP and inflow test the lower deep set bridge plug | 0 | 0 | 4.16 | 23.25 | 0.87 | 21.39 | 19:15 søn 23 jul |  |  |  | MU, RIH wirh upper deepset plug and position while waiting on therminal expansion to decrease. Settiing temperature upper deepset plug 128 deg C. | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 | Upper Deep Barrier plug operation | 110 | 19:15 søn 23 jul | Release from TC, RIH to TD, correlate, set upper Deep set Bridge / Barrier plug in tail pipe at xxxx mMD, line up and perform LP/HP leak test, POOH into TC. | 10 | 10.4 | 10.4 | 6.5 | 0.58 | 21.66 | 01:45 man 24 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 115 | 01:45 man 24 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 2.75 | 0.57 | 21.77 | 04:30 man 24 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 | Tubing cutting | 120 | 04:30 man 24 jul | RU PCH, MU BHA for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 6 | 0.69 | 22.02 | 10:30 man 24 jul |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 2 |  | 125 | 10:30 man 24 jul | Release from TC, RIH to TBG section just above Production Packer , correlate and cut tubing @ XXXX mMD, POOH into TC. | 9 | 9.36 | 9.36 | 6 | 0.55 | 22.27 | 16:30 man 24 jul |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 2 |  | 130 | 16:30 man 24 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 3.25 | 0.55 | 22.41 | 19:45 man 24 jul |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 2 | Barrier plug operation | 135 | 19:45 man 24 jul | RU PCH, MU BHA for Shallow-set Bridge plug plug with IBV & stinger , deploy BHA/PCH and perform well entry pressure test. | 3.5 | 3.64 | 3.64 | 6 | 0.65 | 22.66 | 01:45 tir 25 jul |  |  |  | Cut 100 m of 5/16"monoconductor | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 |  | 140 | 01:45 tir 25 jul | Release from TC. RIH and install shallow set Bridge plug across TRSSSV area allow to keep TRSSSV flapper open , POOH and LD BHA. Perform LP/HP leak test of plug. | 7 | 7.28 | 7.28 | 4.5 | 0.53 | 22.84 | 06:15 tir 25 jul |  |  |  | Ready to retieve hoses and LS prep for jumping stack to Brønn 3 | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 | Well circulation | 145 | 06:15 tir 25 jul | Retrieve Well Service and HC vent hose. | 2 | 2.08 | 2.08 | 3 | 0.57 | 22.97 | 09:15 tir 25 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 2 | Retriveve PCE | 150 | 09:15 tir 25 jul | Recover Lubricator section. | 6 | 6.24 | 6.24 | 7.5 | 0.62 | 23.28 | 16:45 tir 25 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 2 |  | 155 | 16:45 tir 25 jul | RIH WCP RT. | 2 | 2.08 | 2.08 | 3.25 | 0.67 | 23.42 | 20:00 tir 25 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 2 |  | 160 | 20:00 tir 25 jul | Recover WCP 6m above template on Brønn 2 & prepare to jump WCP over to Brønn 3. | 2 | 2.08 | 2.08 | 1 | 0.63 | 23.46 | 21:00 tir 25 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 2 |  | 175 | 21:00 tir 25 jul | Land on Brønn 3 lock and test WCP/XT Controller XT, retrieve WCP RT- LWI adaptor for Field. | 4 | 4.16 | 4.16 | 3 | 0.45 | 23.58 | 00:00 ons 26 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
|  |  | 00:00 ons 26 jul | Repeate the operation on Brønn 3.
|  |  |  | Sum days D10 Actual, End of operation Brønn 2 | 5.75 | 5.98 | 7.17 | 6.42 |  |  |  | 0.22 | 0 | 0
| 7.19 | [10 empty] | 0.03 | 0 | 0 | days
[12 empty] | 0.02 | 0.13 | 0.21 | %
|  |  |  | Brønn 3 | Time estimated |  | CWIS estimate | Actual | ahead- /behind+ | Cumulative
|  | Phase | Start Time | Operation Description | Clean time | Time (D10) | Time | Time | From Best operational time (D10) | Days | Finish Time | WOW (Hrs) | NPT (Hrs) | Scope in | Comments | Gjeldende operasjonell grenseverdi
Brønn 3 | Install PCE | 5 | 00:00 ons 26 jul | Establis GW`s, Deploy LS, lock LLP/WCP connector, install jumpers (El. & Hyd.flying leads), unlock RT, retrieve LS RT, perform pressure testing of WCP and LS. | 8 | 8.32 | 8.32 | 8.5 | 0.18 | 23.94 | 08:30 ons 26 jul |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 3 | THCP operation | 15 | 08:30 ons 26 jul | RU PCH, MU UTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 3.75 | 0.63 | 24.09 | 12:15 ons 26 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 20 | 12:15 ons 26 jul | Release from TC, RIH, land and retreive UTHCP, POOH into TC, retrieve UTHCP BHA, LD BHA. | 5 | 5.2 | 5.2 | 2.25 | -2.95 | 24.19 | 14:30 ons 26 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 25 | 14:30 ons 26 jul | RU PCH, MU LTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 2.5 | -0.62 | 24.29 | 17:00 ons 26 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 30 | 17:00 ons 26 jul | Release from TC, RIH, land and retreive LTHCP, POOH into TC, retrieve LTHCP BHA, LD BHA. | 6 | 6.24 | 6.24 | 3.5 | -2.74 | 24.44 | 20:30 ons 26 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 | Drift run | 40 | 20:30 ons 26 jul | RU PCH, MU BHA for xx" Drift run, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 3.5 | 0.38 | 24.58 | 00:00 tor 27 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 45 | 00:00 tor 27 jul | Release from TC. RIH to tailpipe below production packer, POOH into TC. | 7 | 7.28 | 7.28 | 6 | -1.28 | 24.83 | 06:00 tor 27 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 50 | 06:00 tor 27 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3 | 3 | -0.12 | 24.96 | 09:00 tor 27 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 | Well circulation | 35 | 09:00 tor 27 jul | Rig up 1 x Well Service hose and HC vent hose, attach to WCP. | 4 | 4.16 | 4.16 | 7 | 2.84 | 25.25 | 16:00 tor 27 jul |  | 1.75 |  | NPT Level 1 Identified that hose is to short for connection to WCP when tensioning up GW#2. 1.75 hrs npt 14:30 to 16:15 | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 | Combined IPDT with setting lower deep set bridge plug | 110 | 16:00 tor 27 jul | Line up towards Annulus and pressure test annulus, bleed off, MU BHA # 4 while prepare for bullheading tubing | 0 | 0 | 13 | 3.5 | -2.97 | 25.4 | 19:30 tor 27 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m) + Min wind speed = 6 knot
Brønn 3 |  | 115 | 19:30 tor 27 jul | RU PCH & BHA for Tubing Puncher on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 0 | 1.5 | -2.91 | 25.46 | 21:00 tor 27 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 120 | 21:00 tor 27 jul | Line up Well Service hose towards well and dispace/ bullhead well with 2 ea well tubing volume. | 0 | 0 | 2.6 | 2.75 | -2.8 | 25.57 | 23:45 tor 27 jul |  |  |  | Tubing volume 75 m3 x 2 = 150 m3 | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 125 | 23:45 tor 27 jul | Release from TC, RIH, Correlate, adjust Delta P TBG/Annulus, activate Puncher and punch TBG, POOH 20 m | 0 | 0 | 12 | 10.75 | -2.35 | 26.02 | 10:30 fre 28 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 130 | 10:30 fre 28 jul | Line up Well service hose towards annulus and displaced / bullhead annulus with treated sea water or simular and displace well with 1,2 annulus volume 59 m³ into reservoir. | 0 | 0 | 3 | 1.5 | -2.29 | 26.08 | 12:00 fre 28 jul |  |  |  | Annulus volume 49 x 1,2= 58,8 m3 | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 135 | 12:00 fre 28 jul | Release IPDT and RIH to Lower Deep set bridge plug area, correlate, set deepset bridge plug. POOH into TC | 0 | 0 | 1 | 4.25 | -2.11 | 26.26 | 16:15 fre 28 jul |  | 0.5 |  | NPT Event Level 1:Lost communication with the tool after setting lower deep set plug - no temperature reading available. | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 140 | 16:15 fre 28 jul | POOH into TC. Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 6 | 7 | -1.82 | 26.55 | 23:15 fre 28 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 145 | 23:15 fre 28 jul | RU PCH, MU BHA for Upper Deep -set Bridge / Barrier plug on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 6 | 7.75 | -1.63 | 26.88 | 07:00 lør 29 jul |  |  |  | Meanwhile activity due to thermal expansion. | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 | Upper Deep Barrier plug operation | 150 | 07:00 lør 29 jul | LP/HP and inflow test the lower deep set bridge plug. | 0 | 0 | 23.5 | 14.5 | -1.02 | 27.48 | 21:30 lør 29 jul | 4 |  |  | Experience from Brønn 1 & Brønn 2 high degree of Thermal expansion. NPT Event Level 1: WOW prior to RIH with upper deepset plug. Wind remained below 6 knots for bleeding off 350 bar test pressure. 10am to 14:00 hrs | Wire Line Intervention (Hs= 6,0 m) + Min wind speed = 6 knot
Brønn 3 |  | 155 | 21:30 lør 29 jul | Release from TC, RIH to TD, correlate, set upper Deep set Bridge / Barrier plug in tail pipe at xxxx mMD, line up and perform LP/ HP leak test, POOH into TC. | 10 | 10.4 | 10.4 | 9.25 | -1.07 | 27.86 | 06:45 søn 30 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 160 | 06:45 søn 30 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 2.25 | -1.11 | 27.96 | 09:00 søn 30 jul |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 165 | 09:00 søn 30 jul | RU PCH, MU BHA for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 11.5 | -0.76 | 28.44 | 20:30 søn 30 jul |  | 3.25 |  | ***NPT Event level 1*** Build new cable head and change out cable with back-up drum. | Tubing handling (Hs= 6,0 m)
Brønn 3 | Tubing cutting | 170 | 20:30 søn 30 jul | Release from TC, RIH to TBG section just above Production Packer , correlate and cut tubing @ xxxx mMD, POOH into TC. | 9 | 9.36 | 48 | 8.25 | -0.8 | 28.78 | 04:45 man 31 jul |  | 4 |  | NPT started 00:45 31st of July due to no contact with detonator. ***NPT Event level 1*** Misrun 1: unable to function software program to verify cutter had functioned. POOH and reconfigured toolstring. Misrun 2: Unable to function toolstring downhole. Lost CCL for depth control. NPT started 00:45 hrs 31/07/23 and finished 18:3001/07/23 (41.75 hrs) (Lookahead estimating 45 hrs for this step) | Tubing handling (Hs= 6,0 m)
Brønn 3 |  | 175 | 04:45 man 31 jul | Perform WCP valve test. Retrieve BHA to surface and LD BHA # 6 | 3 | 3.12 | 3.12 | 2.25 | -0.84 | 28.88 | 07:00 man 31 jul |  | 2.25 |  |  | Tubing handling (Hs= 4,0 m)
Brønn 3 |  | 180 | 07:00 man 31 jul | Fault finding on BHA # 6 | 0 | 0 | 0 | 9 | -0.46 | 29.25 | 16:00 man 31 jul |  | 9 |  | Found short in the Knuckle joint | Tubing handling (Hs= 4,0 m)
Brønn 3 |  | 185 | 16:00 man 31 jul | RU PCH, MU BHA # 7 for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 0 | 3.5 | -0.32 | 29.4 | 19:30 man 31 jul |  | 3.5 |  |  | Tubing handling (Hs= 4,0 m)
Brønn 3 |  | 190 | 19:30 man 31 jul | Release from TC, RIH to TBG section just above Production Packer , correlate Tried to cut tubing, no communication with the TS, Decided to POOH into TC | 0 | 0 | 0 | 7.25 | -0.02 | 29.7 | 02:45 tir 01 aug |  | 7.25 |  |  | Tubing handling (Hs= 4,0 m)
Brønn 3 |  | 195 | 02:45 tir 01 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA # 7 | 0 | 0 | 0 | 3 | 0.11 | 29.82 | 05:45 tir 01 aug |  | 2 |  |  | Tubing handling (Hs= 4,0 m)
Brønn 3 |  | 200 | 05:45 tir 01 aug | Fault finding on BHA # 7 | 0 | 0 | 0 | 6.75 | 0.39 | 30.1 | 12:30 tir 01 aug |  | 6.75 |  | Found fault in the swivel joint above the RSS | Tubing handling (Hs= 4,0 m)
Brønn 3 |  | 205 | 12:30 tir 01 aug | RU PCH, MU BHA # 8 for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 0 | 4 | 0.56 | 30.27 | 16:30 tir 01 aug |  | 4 |  |  | Tubing handling (Hs= 4,0 m)
Brønn 3 |  | 210 | 16:30 tir 01 aug | Release from TC, RIH to TBG section just above Production Packer , correlated and cut tubing at 4136 mMD. POOH into TC | 0 | 0 | 0 | 3 | 0.68 | 30.4 | 19:30 tir 01 aug |  | 3 |  |  | Tubing handling (Hs= 4,0 m)
Brønn 3 |  | 215 | 19:30 tir 01 aug | POOH into TC | 0 | 0 | 0 | 2 | 0.77 | 30.48 | 21:30 tir 01 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 3 |  | 215 | 21:30 tir 01 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA # 7 | 0 | 0 | 0 | 2 | 0.85 | 30.56 | 23:30 tir 01 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 3 | Barrier plug operation | 220 | 23:30 tir 01 aug | RU PCH, MU BHA for Shallow-set Bridge plug plug with IBV & stinger , deploy BHA/PCH and perform well entry pressure test. | 3.5 | 3.64 | 4 | 5 | 0.91 | 30.77 | 04:30 ons 02 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 |  | 225 | 04:30 ons 02 aug | Release from TC. RIH and install shallow set Bridge plug across TRSSSV area allow to keep TRSSSV flapper open , POOH and LD BHA. Perform LP/HP leak test of plug. | 7 | 7.28 | 6 | 5 | 0.81 | 30.98 | 09:30 ons 02 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 | Well circulation | 230 | 09:30 ons 02 aug | Retrieve Well Service and HC vent hose. | 2 | 2.08 | 3 | 2 | 0.81 | 31.06 | 11:30 ons 02 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 3 | Retriveve PCE | 235 | 11:30 ons 02 aug | Recover Lubricator section. | 6 | 6.24 | 7 | 8.25 | 0.89 | 31.41 | 19:45 ons 02 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 3 |  | 240 | 19:45 ons 02 aug | RIH WCP RT. | 2 | 2.08 | 3 | 1 | 0.85 | 31.45 | 20:45 ons 02 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 3 |  | 245 | 20:45 ons 02 aug | Recover WCP 6m above template on Brønn 3 & prepare to jump WCP over to Brønn 4. | 2 | 2.08 | 2 | 1 | 0.8 | 31.49 | 21:45 ons 02 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 3 |  | 250 | 21:45 ons 02 aug | Install TDC on Brønn 3. | 1 | 1.04 | 1 | 1 | 0.8 | 31.53 | 22:45 ons 02 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 3 |  | 255 | 22:45 ons 02 aug | Open hatch and Move vessel over Brønn 4. | 2 | 2.08 | 2 | 0.75 | 0.74 | 31.56 | 23:30 ons 02 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 3 |  | 260 | 23:30 ons 02 aug | Land, lock connector on Brønn 4 , retrieve WCP RT- LWI adaptor for Field. | 4 | 4.16 | 4 | 0.5 | 0.59 | 31.58 | 00:00 tor 03 aug |  |  |  | Operations moved to Brønn 4 | Module deployment (Hs= 4,0 m)
|  | 260 | 00:00 tor 03 aug | Repeate the operation on Brønn 4.
|  |  |  | Sum days D10 Actual, End of operation Brønn 3 | 6.13 | 6.37 | 10.7 | 8 | -2.69 |  |  | 0.17 | 1.97 | 0.01
|  |  |  | 7.66 | [7 empty] | 0.03 | 0.31 | 0 | days
[12 empty] | 0.01 | 0.08 | 0 | %
|  |  |  | Brønn 4 | Time estimated |  | CWIS estimate | Actual | ahead- /behind+ | Cumulative
|  | Phase | Start Time | Operation Description | Clean time | Time (D10) | Time | Time | From Best operational time (D10) | Days | Finish Time | WOW (Hrs) | NPT (Hrs) | Scope in | Comments | Gjeldende operasjonell grenseverdi
Brønn 4 | Install PCE | 5 | 00:00 tor 03 aug | Test WCP/XT Controller XT, Establish GW`s on Brønn 4 , Deploy LS, lock LLP/WCP connector, install jumpers (El. & Hyd.flying leads), unlock RT, retrieve LS RT, perform pressure testing of WCP and LS. | 8 | 8.32 | 10 | 18 | 9.68 | 32.33 | 18:00 tor 03 aug |  |  |  | Recovered UTH to change vessel heading due to forecasted weather. | Module deployment (Hs= 4,0 m)
Brønn 4 | THCP operation | 10 | 18:00 tor 03 aug | RU PCH, MU UTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 2 | -1.12 | 32.42 | 20:00 tor 03 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 15 | 20:00 tor 03 aug | Release from TC, RIH, land and retreive UTHCP, POOH into TC, retrieve UTHCP BHA, LD BHA. | 5 | 5.2 | 5.2 | 2 | -3.2 | 32.5 | 22:00 tor 03 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 20 | 22:00 tor 03 aug | RU PCH, MU LTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3 | 1.5 | -1.62 | 32.56 | 23:30 tor 03 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 25 | 23:30 tor 03 aug | Release from TC, RIH, land and retreive LTHCP, POOH into TC, retrieve LTHCP BHA, LD BHA. | 6 | 6.24 | 6.24 | 3.75 | -2.49 | 32.72 | 03:15 fre 04 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Well circulation | 30 | 03:15 fre 04 aug | Rig up 1 x Well Service hose, HC vent hose, attach to WCP and pressure test same | 2 | 2.08 | 4 | 15.75 | 13.67 | 33.38 | 19:00 fre 04 aug |  | 2 | 4.5 | NPT Event Level 1: Changed vessel heading to keep the vessel in limits for helicopter landing. Unable to bleed off annulus pressure and continue with operation. Start 12:30 to End 14:30 Additioanal scope Lubricate and Bleed annulus pressure and pump slops into tubing | Wire Line Intervention (Hs= 6,0 m)+ Min wind speed = 6 knot
Brønn 4 | Well circulation | 35 | 19:00 fre 04 aug | Line up Well Service hose towards well displace / bullhead well with 2 ea well tubing volumes | 3 | 3.12 | 3.12 | 2 | -1.12 | 33.46 | 21:00 fre 04 aug |  |  |  | Tubing volume 70 x 2= 140 m3 Annulus volume 46 x 2=92 m3 | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Tubing to annulus communication operation | 40 | 21:00 fre 04 aug | RU PCH & BHA for Tubing Puncher on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 6.5 | 3.38 | 33.73 | 03:30 lør 05 aug |  | 2.5 |  | NPT Event Level 1 : Puncher /Perforating gun needed to be assembled offshore online time. 2.5 hrs | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 45 | 03:30 lør 05 aug | Release from TC, RIH, Correlate, adjust Delta P TBG/Annulus, activate Puncher and punch TBG, POOH into TC, retrieve BHA, LD BHA. | 8 | 8.32 | 8.32 | 5.25 | -3.07 | 33.95 | 08:45 lør 05 aug |  |  |  | Bullheaded Annulus while POOH | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 50 | 08:45 lør 05 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 3.25 | 0.13 | 34.08 | 12:00 lør 05 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Well circulation | 70 | 12:00 lør 05 aug | Line up Well service hose towards annulus and displace / bullhead well with treated sea water or simular and displace well with 2 ea hole volume xxx m³ into reservoir. | 3 | 3.12 | 3.12 | 2.25 | -0.87 | 34.18 | 14:15 lør 05 aug |  |  |  | Tubing volume 70 x 2= 140 m3 Annulus volume 46 x 2=92 m3 | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Retrieve straddles | 75 | 14:15 lør 05 aug | RU PCH, MU BHA for retrieving APS 563-700 Upper Straddle section, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 4.75 | 1.63 | 34.38 | 19:00 lør 05 aug |  | 2 |  | NPT Event Level 1: Stroker oil needed changed on line time (2 hrs) | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 80 | 19:00 lør 05 aug | Release from TC. RIH to top of Upper straddle, line up and equalize pressure between TBG and Annulus, land /activate BHA and release Upper Straddle section from Lower section pert of , POOH into TC. | 7 | 7.28 | 7.28 | 5 | -2.28 | 34.58 | 00:00 søn 06 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 85 | 00:00 søn 06 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 3.5 | 0.38 | 34.73 | 03:30 søn 06 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 90 | 03:30 søn 06 aug | RU PCH, MU BHA for retrieving APS 563-700 Lower straddle section, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 10.75 | 7.63 | 35.18 | 14:15 søn 06 aug |  | 8 |  | NPT Level 1: Prepared and changed upper sheave wheel for DUS3 in - line tensioner in MHT due to damaged bearing (8 hrs) | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 95 | 14:15 søn 06 aug | Release from TC. RIH to top of bottom straddle, land/activate BHA and release bottom straddle, POOH into TC. | 7 | 7.28 | 7.28 | 10.75 | 3.47 | 35.63 | 01:00 man 07 aug |  | 6.75 |  | NPT Level 1: Stroker failure at 1350m prior to latching Straddle (6.75 hrs) | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 100 | 01:00 man 07 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 2.25 | -0.87 | 35.72 | 03:15 man 07 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 105 | 03:15 man 07 aug | RU PCH, MU BHA for retrieving APS 563-700 Single run straddle, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 1.5 | -1.62 | 35.78 | 04:45 man 07 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 110 | 04:45 man 07 aug | Release from TC. RIH to top of straddle, equalize TBG/Annulus if needed, land/activate BHA and release straddle, POOH into TC. | 7 | 7.28 | 7.28 | 2.25 | -5.03 | 35.88 | 07:00 man 07 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 115 | 07:00 man 07 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 3.25 | 0.13 | 36.01 | 10:15 man 07 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Lower Deep Barrier plug operation | 140 | 10:15 man 07 aug | RU PCH, MU BHA for Lower Deep -set Bridge / Barrier plug on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 4 | 0.88 | 36.18 | 14:15 man 07 aug |  | 0.5 |  | NPT Level 1: PCH and BHA twisted over umbilicals due to current. | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 145 | 14:15 man 07 aug | Release from TC, RIH to TD, correlate, set Lower Deep set Bridge / Barrier plug in tail pipe at xxxx mMD, line up and perform Inflow or HP leak test, POOH into TC. | 10 | 10.4 | 10.4 | 5.5 | -4.9 | 36.41 | 19:45 man 07 aug |  |  |  | Pressure testing parallel activity while changing out BHA's | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 150 | 19:45 man 07 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 3.25 | 0.13 | 36.54 | 23:00 man 07 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Upper Deep Barrier plug operation | 155 | 23:00 man 07 aug | RU PCH, MU BHA for Upper Deep -set Bridge / Barrier plug on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 4.75 | 1.63 | 36.74 | 03:45 tir 08 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 160 | 03:45 tir 08 aug | Release from TC, RIH to TD, correlate, set upper Deep set Bridge / Barrier plug in tail pipe at xxxx mMD, line up and perform LP/ HP leak test, POOH into TC. | 10 | 10.4 | 10.4 | 7.75 | -2.65 | 37.06 | 11:30 tir 08 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 165 | 11:30 tir 08 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 2.5 | -0.62 | 37.17 | 14:00 tir 08 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Tubing cutting | 170 | 14:00 tir 08 aug | Wait on Weather | 0 | 0 | 0 | 41.5 | 41.5 | 38.9 | 07:30 tor 10 aug | 41.5 |  |  | NPT Event Level 1: WOW to deploy tubing cutter. 14:00 hrs 08/08 - 07:30 10/8 41.5 hrs | Tubing handling (Hs= 4,0 m)
Brønn 4 |  | 170 | 07:30 tor 10 aug | RU PCH, MU BHA for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 2.5 | -0.62 | 39 | 10:00 tor 10 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 4 |  | 175 | 10:00 tor 10 aug | Release from TC, RIH to TBG section just above Production Packer , correlate and cut tubing @ xxx mMD, POOH into TC. | 9 | 9.36 | 9.36 | 2.75 | -6.61 | 39.11 | 12:45 tor 10 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 4 |  | 176 | 12:45 tor 10 aug | POOH into TC. After dscovery of tubing cutting failure | 0 | 0 | 0 | 3.25 | 3.25 | 39.25 | 16:00 tor 10 aug |  | 3.75 |  | NPT Event 1 faiure in Explosives (Altus) | Tubing handling (Hs= 4,0 m)
Brønn 4 |  | 177 | 16:00 tor 10 aug | Built new socket on GW#2 after removing 420 m damaged wire | 0 | 0 | 0 | 4.75 | 4.75 | 39.45 | 20:45 tor 10 aug |  | 4.75 |  | NPT Event Level 2: Built new socket on GW#2 after removing 420m damaged wire (TIOS) | Tubing handling (Hs= 4,0 m)
Brønn 4 |  | 180 | 20:45 tor 10 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 1.75 | -1.37 | 39.52 | 22:30 tor 10 aug |  | 1.75 |  | NPT Event 1 faiure in Explosives (Altus) | Tubing handling (Hs= 4,0 m)
Brønn 4 | Barrier plug operation | 185 | 22:30 tor 10 aug | RU PCH, MU BHA for Shallow-set Bridge plug plug with IBV & stinger , deploy BHA/PCH and perform well entry pressure test. | 3.5 | 3.64 | 3.64 | 4 | 0.36 | 39.69 | 02:30 fre 11 aug |  | 4 |  | NPT Event 1 faiure in Explosives (Altus) | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 190 | 02:30 fre 11 aug | Release from TC. RIH and install shallow set Bridge plug across TRSSSV area allow to keep TRSSSV flapper open , Tool faiure on Setting tool | 7 | 7.28 | 7.28 | 0.5 | -6.78 | 39.71 | 03:00 fre 11 aug |  | 0.5 |  | NPT Event 1 faiure in Explosives (Altus) | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 195 | 03:00 fre 11 aug | POOH with failed ME 572-700 ME plug and LD plug | 0 | 0 | 3 | 8 | 8 | 40.04 | 11:00 fre 11 aug |  | 3 |  | NPT Event 2 572-700 ME bridge plug EST failure | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Contingency Tubing cutting | 200 | 11:00 fre 11 aug | RU PCH, MU BHA for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 3.75 | 3.75 | 40.2 | 14:45 fre 11 aug |  | 3.75 |  | NPT Event 1 faiure in Explosives (Altus) | Tubing handling (Hs= 4,0 m)
Brønn 4 |  | 205 | 14:45 fre 11 aug | Release from TC, RIH to TBG section just above Production Packer , correlate and cut tubing @ xxx mMD, | 0 | 0 | 4 | 5 | 5 | 40.41 | 19:45 fre 11 aug |  | 5 |  | NPT Event 1 faiure in Explosives (Altus) | Tubing handling (Hs= 4,0 m)
Brønn 4 |  | 210 | 19:45 fre 11 aug | POOH with Cutter and LD Cutter BHA | 0 | 0 | 5 | 6.75 | 6.75 | 40.69 | 02:30 lør 12 aug |  | 6.75 |  | NPT Event 1 faiure in Explosives (Altus) | Tubing handling (Hs= 4,0 m)
Brønn 4 | Barrier plug operation | 215 | 02:30 lør 12 aug | RU PCH, MU BHA for Shallow Bridgle plug tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3 | 4.25 | 4.25 | 40.86 | 06:45 lør 12 aug |  | 4.25 |  | NPT Event 2 572-700 ME bridge plug EST failure (Interwell) | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 |  | 220 | 06:45 lør 12 aug | Release from TC. RIH and install shallow set Bridge plug across TRSSSV area allow to keep TRSSSV flapper open, POOH & LD BHA , LP & HP test plug | 0 | 0 | 2 | 6 | 6 | 41.11 | 12:45 lør 12 aug |  | 1.25 |  | NPT Event 2 572-700 ME bridge plug EST failure ends when Deepset bridge plug has been set (Interwell) | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Well circulation | 195 | 12:45 lør 12 aug | Retrieve Well Service and HC vent hose. | 2 | 2.08 | 2.08 | 1.25 | -0.83 | 41.17 | 14:00 lør 12 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 4 | Retriveve PCE | 200 | 14:00 lør 12 aug | Recover Lubricator section. | 6 | 6.24 | 6.24 | 7.5 | 1.26 | 41.48 | 21:30 lør 12 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 4 |  | 205 | 21:30 lør 12 aug | RIH WCP RT. | 2 | 2.08 | 2.08 | 2.5 | 0.42 | 41.58 | 00:00 søn 13 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 4 |  | 210 | 00:00 søn 13 aug | Recover WCP to surface and park same. | 6 | 6.24 | 6.24 | 2.5 | -3.74 | 41.69 | 02:30 søn 13 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 4 |  | 215 | 02:30 søn 13 aug | Install TDC. | 1 | 1.04 | 1.04 | 0.5 | -0.54 | 41.71 | 03:00 søn 13 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 4 |  | 220 | 03:00 søn 13 aug | Close all hatches. | 3 | 3.12 | 3.12 | 1.75 | -1.37 | 41.78 | 04:45 søn 13 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 4 |  | 225 | 04:45 søn 13 aug | Retrieve ROV baskets. | 5 | 5.2 | 5.2 | 3 | -2.2 | 41.91 | 07:45 søn 13 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
|  |  |  | Sum days D10 Actual, End of operation Brønn 4 | 7.77 | 8.08 | 10.06 | 11.79 | 3.71 |  |  | 1.73 | 2.98 | 0.19
|  | 9.71 | [9 empty] | 0.27 | 0.46 | 0.03 | days
|  |  |  | Total Days D10 end of operation A template | 29.69 | 30.75 | 45.32 | 43.38 |  |  |  | 0.07 | 0.13 | 0.01 | %
|  |  |  | Brønn 5 | Time estimated |  | CWIS estimate | Actual | ahead- /behind+ | Cumulative
|  | Phase | Start Time | Operation Description | Clean time | Time (D10) | Time | Time | From Best operational time (D10) | Days | Finish Time P10 | WOW (Hrs) | NPT (Hrs) | Scope in | Comments | Gjeldende operasjonell grenseverdi
Brønn 5 | Prepare well for PCE deployment | 5 | 19:00 man 14 aug | Perform DP Trials and handover well from Field. | 2 | 2.08 | 2.08 | 2 | -0.08 | 43.46 | 21:00 man 14 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 5 |  | 10 | 21:00 man 14 aug | Deploy ROV, Deploy ROV baskets, Carry out "As Found" Survey & place transponders. Open well protection structure hatches on Brønn 7. | 6 | 6.24 | 6.24 | 5.5 | -0.74 | 43.69 | 02:30 tir 15 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 5 |  | 15 | 02:30 tir 15 aug | Remove TDC and carrie out acid treatment. | 3 | 3.12 | 3.12 | 4.25 | 1.13 | 43.86 | 06:45 tir 15 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 5 |  | 20 | 06:45 tir 15 aug | Skid in WCP, Install VX seal gasket and establish GW`s. | 3 | 3.12 | 3.12 | 1.75 | -1.37 | 43.94 | 08:30 tir 15 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 5 | Install PCE | 25 | 08:30 tir 15 aug | Deploy WCP, land WCP, lock connector, retrieve WCP RT | 7 | 7.28 | 7.28 | 6 | -1.28 | 44.19 | 14:30 tir 15 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 5 |  | 30 | 14:30 tir 15 aug | Establis GW`s, Deploy LS, lock LLP/WCP connector, install jumpers (El. & Hyd.flying leads), unlock RT, retrieve LS RT, perform pressure testing of WCP and LS. | 8 | 8.32 | 8.32 | 6.75 | -1.57 | 44.47 | 21:15 tir 15 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 5 | THCP operation | 35 | 21:15 tir 15 aug | RU PCH, MU UTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 2.25 | -0.87 | 44.56 | 23:30 tir 15 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 40 | 23:30 tir 15 aug | Release from TC, RIH, land and retreive UTHCP, POOH into TC, retrieve UTHCP BHA, LD BHA. | 5 | 5.2 | 5.2 | 2.75 | -2.45 | 44.68 | 02:15 ons 16 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 45 | 02:15 ons 16 aug | RU PCH, MU LTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 1.25 | -1.87 | 44.73 | 03:30 ons 16 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 50 | 03:30 ons 16 aug | Release from TC, RIH, land and retreive LTHCP, POOH into TC, retrieve LTHCP BHA, LD BHA. | 6 | 6.24 | 6.24 | 4 | -2.24 | 44.9 | 07:30 ons 16 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 | Well circulation | 55 | 07:30 ons 16 aug | Rig up 1 x Well Service hose and HC vent hose, attach to WCP. | 2 | 2.08 | 2.08 | 3 | 0.92 | 45.02 | 10:30 ons 16 aug |  |  |  | Incuded bleeding of Annulus to 100bar. | Wire Line Intervention (Hs= 6,0 m) + Min wind speed = 6 knot
Brønn 5 |  | 130 | 10:30 ons 16 aug | Line up towards Annulus and test annulus, bleed off, MU BHA # 3 while prepare for bullheading tubing | 0 | 0 | 3.5 | 3 | 3 | 45.15 | 13:30 ons 16 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m) + Min wind speed = 6 knot
Brønn 5 |  | 135 | 13:30 ons 16 aug | RU PCH & BHA for Tubing Puncher on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 1.5 | 1.25 | 1.25 | 45.2 | 14:45 ons 16 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 | Combined IPDT with setting lower deep set bridge plug | 140 | 14:45 ons 16 aug | Line up Well Service hose towards well and dispace/ bullhead well with 1,2 ea well tubing volume. ( 92 m3) | 0 | 0 | 2.75 | 1.25 | 1.25 | 45.25 | 16:00 ons 16 aug |  |  |  | Tubing volume 77 x 1,5 = 92 m3 Annulus volume 45.6 x 1,2= 55 m3 | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 145 | 16:00 ons 16 aug | Release from TC, RIH, Correlate, adjust Delta P TBG/Annulus, activate Puncher and punch TBG, POOH 20 m | 0 | 0 | 10.75 | 8 | 8 | 45.58 | 00:00 tor 17 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 150 | 00:00 tor 17 aug | Line up Well service hose towards annulus and displaced / bullhead annulus with treated sea water or simular and displace well with 1,2 annulus volume 55 m³ into reservoir. | 0 | 0 | 1.5 | 1 | 1 | 45.63 | 01:00 tor 17 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 155 | 01:00 tor 17 aug | Release IPDT and RIH to Lower Deep set bridge plug area, correlate, set deepset bridge plug. POOH into TC | 0 | 0 | 4.25 | 3.5 | 3.5 | 45.77 | 04:30 tor 17 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 160 | 04:30 tor 17 aug | POOH into TC. Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 7 | 6 | 6 | 46.02 | 10:30 tor 17 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 | Upper Deep Barrier plug operation | 130 | 10:30 tor 17 aug | RU PCH, MU BHA for Upper deep set bridge plugl on E-line, deploy BHA/PCH and perform well entry pressure test. RIH to 773m. Performed LP/HP and inflow test on Lower deep set plug | 3 | 3.12 | 3.12 | 11.25 | 8.13 | 46.49 | 21:45 tor 17 aug |  |  |  | Included pressure testing of Lower deepset plug. Waitring for therminal expansin to achieve good test on plug prior to RIH and set the upper deep set plug. | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 135 | 21:45 tor 17 aug | Lost power on vessel due to shut-down of DG 2. Pulled WL BHA #4 back in TC. Sorted out DG 2 issue and RIH to 773m with WL BHA #4. | 0 | 0 | 7.5 | 7.5 | 7.5 | 46.8 | 05:15 fre 18 aug |  | 7.5 |  | NPT, Generator shut down | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 135 | 05:15 fre 18 aug | Release from TC, RIH to TD, correlate, set upper Deep set Bridge / Barrier plug in tail pipe at 4132mMD, line up and perform Inflow or HP leak test, POOH into TC. | 10 | 10.4 | 10.4 | 8 | -2.4 | 47.14 | 13:15 fre 18 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 140 | 13:15 fre 18 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 3 | -0.12 | 47.26 | 16:15 fre 18 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 | Tubing cutting | 135 | 16:15 fre 18 aug | RU PCH, MU BHA for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 5.75 | 2.63 | 47.5 | 22:00 fre 18 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 5 |  | 140 | 22:00 fre 18 aug | Release from TC, RIH to TBG section just above Production Packer, correlate and cut tubing, POOH @ 4111mMD into TC. | 9 | 9.36 | 9.36 | 5.5 | -3.86 | 47.73 | 03:30 lør 19 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 5 |  | 145 | 03:30 lør 19 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 2.5 | -0.62 | 47.83 | 06:00 lør 19 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 5 | Camera run | 150 | 06:00 lør 19 aug | RU PCH, MU BHA for Vision IO Camera run, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 6 | 6 | 48.08 | 12:00 lør 19 aug |  | 2 |  | Included 2 hrs NPT recovering Camera to apply protection bag. | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 155 | 12:00 lør 19 aug | Release from TC. RIH to top of cut below DHPG, perform visulationon cut, POOH into TC. | 0 | 0 | 7.12 | 5.75 | 5.75 | 48.32 | 17:45 lør 19 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 160 | 17:45 lør 19 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 3.12 | 2 | 2 | 48.41 | 19:45 lør 19 aug |  |  |  | Vison IO camera run replaces Drift run | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 | Barrier plug operation | 165 | 19:45 lør 19 aug | RU PCH, MU BHA for Shallow-set Bridge plug plug with IBV & stinger , deploy BHA/PCH and perform well entry pressure test. | 3.5 | 3.64 | 3.64 | 8 | 4.36 | 48.74 | 03:45 søn 20 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 170 | 03:45 søn 20 aug | Release from TC. RIH and install shallow set Bridge plug across TRSSSV area allow to keep TRSSSV flapper open , POOH and LD BHA. Perform LP/HP leak test of plug. | 7 | 7.28 | 7.28 | 5.5 | -1.78 | 48.97 | 09:15 søn 20 aug |  |  |  | Included offline test of AMV & XOV | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 | Well circulation | 175 | 09:15 søn 20 aug | Retrieve Well Service and HC vent hose. | 2 | 2.08 | 2.08 | 2 | -0.08 | 49.05 | 11:15 søn 20 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 | Retriveve PCE | 180 | 11:15 søn 20 aug | Recover Lubricator section. | 6 | 6.24 | 6.24 | 5.25 | -0.99 | 49.27 | 16:30 søn 20 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 185 | 16:30 søn 20 aug | RIH WCP RT. | 2 | 2.08 | 2.08 | 3.75 | 1.67 | 49.43 | 20:15 søn 20 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 190 | 20:15 søn 20 aug | Recover WCP 6 m above template on B-2H & prepare to jump WCP over to Brønn 7. | 2 | 2.08 | 2.08 | 0.5 | -1.58 | 49.45 | 20:45 søn 20 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 5 |  | 205 | 20:45 søn 20 aug | Land, lock onto Brønn 6 and test WCP/XT Controller XT, retrieve WCP RT- LWI adaptor for Field. | 4 | 4.16 | 4.16 | 3.25 | -0.91 | 49.58 | 00:00 man 21 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
|  | 210 | 00:00 man 21 aug | Repeate the operation on Brønn 6.
|  |  |  | Sum days D10, D50 & D90 Actual, End of operation B-2H | 6.56 | 6.83 | 9 | 6.21 | -0.62 |  |  | 0 | 0.4 | 0
| 8.2 | [10 empty] | 0 | 0.06 | 0 | days
[12 empty] | 0 | 0.02 | 0 | %
|  |  |  | Brønn 6 | Time estimated |  | CWIS estimate | Actual | ahead- /behind+ | Cumulative
|  | Phase | Start Time | Operation Description | Clean time | Time (D10) | Time | Time | From Best operational time (D10) | Days | Finish Time | WOW (Hrs) | NPT (Hrs) | Scope in | Comments | Gjeldende operasjonell grenseverdi
Brønn 6 | Install PCE | 5 | 00:00 man 21 aug | Establis GW`s on Brønn 7, Deploy LS, lock LLP/WCP connector, install jumpers (El. & Hyd.flying leads), unlock RT, retrieve LS RT, perform pressure testing of WCP and LS. | 8 | 8.32 | 8.32 | 8 | -0.32 | 49.92 | 08:00 man 21 aug |  |  |  | Ongoing Operations at 06:00 21/08/23 | Module deployment (Hs= 4,0 m)
Brønn 6 |  | 15 | 08:00 man 21 aug | RU PCH, MU UTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 5 | 5.2 | 5.2 | 3.25 | -1.95 | 50.05 | 11:15 man 21 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 | THCP operation | 20 | 11:15 man 21 aug | Release from TC, RIH, land and retreive UTHCP, POOH into TC, retrieve UTHCP BHA, LD BHA. | 3 | 3.12 | 3.12 | 2.5 | -0.62 | 50.16 | 13:45 man 21 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 25 | 13:45 man 21 aug | RU PCH, MU LTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 5 | 5.2 | 5.2 | 2.5 | -2.7 | 50.26 | 16:15 man 21 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 30 | 16:15 man 21 aug | Release from TC, RIH, land and retreive LTHCP, POOH into TC, retrieve LTHCP BHA, LD BHA. | 3 | 3.12 | 3.12 | 4.5 | 1.38 | 50.45 | 20:45 man 21 aug |  |  |  | Included equilising TRSSSV | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 | Well circulation | 35 | 20:45 man 21 aug | Rig up 1 x Well Service hose and HC vent hose, attach to WCP. | 3 | 3.12 | 3.12 | 5 | 1.88 | 50.66 | 01:45 tir 22 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 | Combined IPDT with setting lower deep set bridge plug | 110 | 01:45 tir 22 aug | Line up towards Annulus and test annulus, bleed off, MU BHA # 3 while prepare for bullheading tubing | 0 | 0 | 3.5 | 2 | 2 | 50.74 | 03:45 tir 22 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m) + Min wind speed = 6 knot
Brønn 6 |  | 115 | 03:45 tir 22 aug | RU PCH & BHA for Tubing Puncher on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 1.5 | 1.75 | 1.75 | 50.81 | 05:30 tir 22 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 120 | 05:30 tir 22 aug | Line up Well Service hose towards well and dispace/ bullhead well with 1,5 ea well tubing volume. | 0 | 0 | 2.75 | 2 | 2 | 50.9 | 07:30 tir 22 aug |  |  |  | Tubing volume 74 x 1,2= 89 m3 Annulus volume 46 x1, 2= 55 m3 | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 125 | 07:30 tir 22 aug | Release from TC, RIH, Correlate, adjust Delta P TBG/Annulus, activate Puncher and punch TBG, POOH 20 m | 0 | 0 | 10.75 | 5.5 | 5.5 | 51.13 | 13:00 tir 22 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 130 | 13:00 tir 22 aug | Line up Well service hose towards annulus and displaced / bullhead annulus with treated sea water or simular and displace well with 1,2 annulus volume 55 m³ into reservoir. | 0 | 0 | 1.5 | 2.5 | 2.5 | 51.23 | 15:30 tir 22 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 135 | 15:30 tir 22 aug | Release IPDT and RIH to Lower Deep set bridge plug area, correlate, set deepset bridge plug. POOH into TC | 0 | 0 | 4.25 | 3.5 | 3.5 | 51.38 | 19:00 tir 22 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 140 | 19:00 tir 22 aug | POOH into TC. Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 7 | 6.5 | 6.5 | 51.65 | 01:30 ons 23 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 | Upper Deep Barrier plug operation | 110 | 01:30 ons 23 aug | RU PCH, MU BHA for Upper Deep -set Bridge / Barrier plug on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 3.5 | 0.38 | 51.79 | 05:00 ons 23 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 115 | 05:00 ons 23 aug | Perform LP/HP lower plug. Release from TC, RIH to TD, correlate, set Lower Deep set Bridge / Barrier plug in tail pipe at 4150 mMD, line up and perform LP/ HP leak test, POOH into TC. | 10 | 10.4 | 10.4 | 14.25 | 3.85 | 52.39 | 19:15 ons 23 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 120 | 19:15 ons 23 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 3.5 | 0.38 | 52.53 | 22:45 ons 23 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 | Tubing cutting | 125 | 22:45 ons 23 aug | RU PCH, MU BHA for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 4 | 0.88 | 52.7 | 02:45 tor 24 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 6 |  | 130 | 02:45 tor 24 aug | Release from TC, RIH to TBG section just above Production Packer, correlate and cut tubing @ 4129 mMD, POOH into TC. | 8 | 8.32 | 8.32 | 5.5 | -2.82 | 52.93 | 08:15 tor 24 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 6 |  | 135 | 08:15 tor 24 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 2.75 | -0.37 | 53.04 | 11:00 tor 24 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 6 | Camera run | 140 | 11:00 tor 24 aug | Built new cable head due to LIH RU PCH, MU BHA for Vision IO Camera run, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 8.5 | 8.5 | 53.4 | 19:30 tor 24 aug |  |  |  | Vison IO camera run replaces Drift run | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 145 | 19:30 tor 24 aug | Release from TC. RIH to top of cut below DHPG, perform visulationon cut, POOH into TC. | 0 | 0 | 7.12 | 5.5 | 5.5 | 53.63 | 01:00 fre 25 aug |  |  |  | Vison IO camera run replaces Drift run | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 150 | 01:00 fre 25 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 3.12 | 3.5 | 3.5 | 53.77 | 04:30 fre 25 aug |  |  |  | Vison IO camera run replaces Drift run | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 | Barrier plug operation | 140 | 04:30 fre 25 aug | RU PCH, MU BHA for Shallow-set Bridge plug plug with IBV & stinger , deploy BHA/PCH and perform well entry pressure test. | 3.5 | 3.64 | 3.64 | 3.5 | -0.14 | 53.92 | 08:00 fre 25 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 |  | 145 | 08:00 fre 25 aug | Release from TC. RIH and install shallow set Bridge plug across TRSSSV area allow to keep TRSSSV flapper open , POOH and LD BHA. Perform LP/HP leak test of plug. | 7 | 7.28 | 7.28 | 6.25 | -1.03 | 54.18 | 14:15 fre 25 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 | Well circulation | 150 | 14:15 fre 25 aug | Retrieve Well Service and HC vent hose. | 2 | 2.08 | 2.08 | 1.5 | -0.58 | 54.24 | 15:45 fre 25 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 6 | Retriveve PCE | 155 | 15:45 fre 25 aug | Recover Lubricator section. | 6 | 6.24 | 6.24 | 3 | -3.24 | 54.36 | 18:45 fre 25 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 6 |  | 160 | 18:45 fre 25 aug | Repaired breaks on GW#1 m/w P/T LS and lower VX. Est 3 x GWs and RIH WCP RT. | 2 | 2.08 | 2.08 | 6.75 | 4.67 | 54.65 | 01:30 lør 26 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 6 |  | 165 | 01:30 lør 26 aug | Recover WCP 6m above template on Brønn 6 & prepare to jump WCP over to Brønn 7. | 2 | 2.08 | 2.08 | 2 | -0.08 | 54.73 | 03:30 lør 26 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 6 |  | 180 | 03:30 lør 26 aug | Land, lock on Brønn 7 and test WCP/XT Controller XT, retrieve WCP RT- LWI adaptor for Field. Establish guidewires onto Brønn 7. Complete testing of LS. | 4 | 4.16 | 4.16 | 6 | 1.84 | 54.98 | 09:30 lør 26 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
|  |  | 09:30 lør 26 aug | Repeat the operation on Brønn 7.
|  |  |  | Sum days D10, D50 & D90 Actual, End of operation Brønn 6 | 5.85 | 6.09 | 7.95 | 5.4 | -0.69 |  |  | 0 | 0 | 0
| 7.32 | [10 empty] | 0 | 0 | 0 | days
[12 empty] | 0 | 0 | 0 | %
|  |  |  | Brønn 7 | Time estimated |  | CWIS estimate | Actual | ahead- /behind+ | Cumulative
|  | Phase | Start Time | Operation Description | Clean time | Time (D10) | Time | Time | From Best operational time (D10) | Days | Finish Time | WOW (Hrs) | NPT (Hrs) | Scope in | Comments | Gjeldende operasjonell grenseverdi
Brønn 7 | Install PCE | 5 | 09:30 lør 26 aug | Deploy LS, lock LLP/WCP connector, install jumpers (El. & Hyd.flying leads), unlock RT, retrieve LS RT, perform pressure testing of WCP and LS. Including 14-day barrier testing. | 8 | 8.32 | 8.32 | 7.25 | -1.07 | 55.28 | 16:45 lør 26 aug |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 7 | THCP operation | 10 | 16:45 lør 26 aug | RU PCH, MU UTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 2.75 | -0.37 | 55.4 | 19:30 lør 26 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 15 | 19:30 lør 26 aug | Release from TC, RIH, land and retreive UTHCP, POOH into TC, retrieve UTHCP BHA, LD BHA. | 5 | 5.2 | 5.2 | 2.5 | -2.7 | 55.5 | 22:00 lør 26 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 20 | 22:00 lør 26 aug | RU PCH, MU LTHCP BHA, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 1.5 | -1.62 | 55.56 | 23:30 lør 26 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 25 | 23:30 lør 26 aug | Release from TC, RIH, land and retreive LTHCP, POOH into TC, retrieve LTHCP BHA, LD BHA. | 6 | 6.24 | 6.24 | 5 | -1.24 | 55.77 | 04:30 søn 27 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 | Well circulation | 30 | 04:30 søn 27 aug | Rig up 1 x Well Service hose and HC vent hose, attach to WCP. | 3 | 3.12 | 3.12 | 4 | 0.88 | 55.94 | 08:30 søn 27 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 | Combined IPDT with setting lower deep set bridge plug | 105 | 08:30 søn 27 aug | Line up towards Annulus and test annulus, bleed off, MU BHA # 4 while prepare for bullheading tubing | 0 | 0 | 3.5 | 2 | 2 | 56.02 | 10:30 søn 27 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 110 | 10:30 søn 27 aug | RU PCH & BHA for Tubing Puncher on E-line, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 1.5 | 2 | 2 | 56.1 | 12:30 søn 27 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 115 | 12:30 søn 27 aug | Line up Well Service hose towards well and bullhead well with 1,5 ea well tubing volume. | 0 | 0 | 2.75 | 3 | 3 | 56.23 | 15:30 søn 27 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 120 | 15:30 søn 27 aug | Release from TC, RIH, Correlate, adjust Delta P TBG/Annulus, activate Puncher and punch TBG, POOH 20 m | 0 | 0 | 8 | 17.5 | 17.5 | 56.96 | 09:00 man 28 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 125 | 09:00 man 28 aug | Unable to pass 2920m. POOH into TC. Well exit test. Retrieve & lay down BHA #3. | 0 | 0 | 8 | 8.5 | 8.5 | 57.31 | 17:30 man 28 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 130 | 17:30 man 28 aug | Make up and deploy BHA #4: IPDT & HEX Plug. Well entry test. | 0 | 0 | 4 | 6 | 6 | 57.56 | 23:30 man 28 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 135 | 23:30 man 28 aug | RIH. Correlate. Set pressure differential. Punch 5x holes in tubing. | 0 | 0 | 8 | 5 | 5 | 57.77 | 04:30 tir 29 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 140 | 04:30 tir 29 aug | Bullhead annulus. | 0 | 0 | 2 | 1.25 | 1.25 | 57.82 | 05:45 tir 29 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 145 | 05:45 tir 29 aug | Correlate and set Lower Deep Set plug. | 0 | 0 | 3.5 | 1 | 1 | 57.86 | 06:45 tir 29 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 150 | 06:45 tir 29 aug | POOH into TC. Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 6 | 7 | 7 | 58.16 | 13:45 tir 29 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 | Upper Deep Barrier plug operation | 155 | 13:45 tir 29 aug | RU PCH, MU BHA for Upper Deep -set Bridge / Barrier plug on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 3.12 | 5.75 | 2.63 | 58.4 | 19:30 tir 29 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 160 | 19:30 tir 29 aug | Pressure test and inflow test Lower Deepset Plug. | 0 | 0 | 6 | 1.5 | 1.5 | 58.46 | 21:00 tir 29 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 160 | 21:00 tir 29 aug | Release from TC, RIH to TD, correlate, set upper Deep set Bridge / Barrier plug in tail pipe. Line up and perform Inflow or HP leak test, POOH into TC. | 10 | 10.4 | 10.4 | 9.75 | -0.65 | 58.86 | 06:45 ons 30 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 165 | 06:45 ons 30 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 2 | -1.12 | 58.95 | 08:45 ons 30 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 | Tubing cutting | 170 | 08:45 ons 30 aug | RU PCH, cut cable, build new cable head, test and MU BHA for Tubing Cutting tool on E-line, deploy BHA/PCH and perform well entry pressure test. | 3 | 3.12 | 5 | 7 | 3.88 | 59.24 | 15:45 ons 30 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 7 |  | 175 | 15:45 ons 30 aug | Release from TC, RIH to TBG section just above Production Packer, correlate and cut tubing @ 4056 mMD, POOH into TC. | 8 | 8.32 | 8.32 | 5.5 | -2.82 | 59.47 | 21:15 ons 30 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 7 |  | 180 | 21:15 ons 30 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 3 | 3.12 | 3.12 | 2.5 | -0.62 | 59.57 | 23:45 ons 30 aug |  |  |  |  | Tubing handling (Hs= 4,0 m)
Brønn 7 | Camera run | 185 | 23:45 ons 30 aug | RU PCH, MU BHA for Vision IO Camera run, deploy BHA/PCH and perform well entry pressure test. | 0 | 0 | 3.12 | 2.5 | 2.5 | 59.68 | 02:15 tor 31 aug |  |  |  | Vison IO camera run replaces Drift run | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 190 | 02:15 tor 31 aug | Release from TC. RIH to top of cut below DHPG, perform visulationon cut, POOH into TC. | 0 | 0 | 7.12 | 4.25 | 4.25 | 59.85 | 06:30 tor 31 aug |  |  |  | Vison IO camera run replaces Drift run | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 195 | 06:30 tor 31 aug | Perform WCP valve test. Retrieve BHA to surface and LD BHA. | 0 | 0 | 3.12 | 3.5 | 3.5 | 60 | 10:00 tor 31 aug |  |  |  | Vison IO camera run replaces Drift run | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 | Barrier plug operation | 185 | 10:00 tor 31 aug | RU PCH, MU BHA for Shallow-set Bridge plug plug with IBV & stinger, deploy BHA/PCH and perform well entry pressure test. | 3.5 | 3.64 | 3.64 | 2.5 | -1.14 | 60.1 | 12:30 tor 31 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 |  | 190 | 12:30 tor 31 aug | Release from TC. RIH and install shallow set Bridge plug across TRSSSV area allow to keep TRSSSV flapper open , POOH and LD BHA. Perform HP leak test of plug and AMV barrier. | 7 | 7.28 | 6 | 5 | -2.28 | 60.31 | 17:30 tor 31 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 | Well circulation | 195 | 17:30 tor 31 aug | Retrieve Well Service and HC vent hose. | 2 | 2.08 | 2.08 | 3 | 0.92 | 60.44 | 20:30 tor 31 aug |  |  |  |  | Wire Line Intervention (Hs= 6,0 m)
Brønn 7 | Retriveve PCE | 200 | 20:30 tor 31 aug | Recover Lubricator section. | 6 | 6.24 | 4 | 5 | -1.24 | 60.65 | 01:30 fre 01 sep |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 7 |  | 205 | 01:30 fre 01 sep | RIH WCP RT. | 2 | 2.08 | 2.08 | 1.5 | -0.58 | 60.71 | 03:00 fre 01 sep |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 7 |  | 210 | 03:00 fre 01 sep | Recover WCP to surface and park same. | 6 | 6.24 | 6.24 | 5 | -1.24 | 60.92 | 08:00 fre 01 sep |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 7 |  | 220 | 08:00 fre 01 sep | Close all hatches. | 3 | 3.12 | 2 | 2 | -1.12 | 61 | 10:00 fre 01 sep |  |  |  |  | Module deployment (Hs= 4,0 m)
Brønn 7 |  | 225 | 10:00 fre 01 sep | Retrieve ROV baskets. | 5 | 5.2 | 4 | 5 | -0.2 | 61.21 | 15:00 fre 01 sep |  |  |  |  | Module deployment (Hs= 4,0 m)
|  |  |  | Sum days D10, D50 & D90 Actual, End of operation Brønn 7 | 7.23 | 7.47 | 10.11 | 7.55 | 0.91 |  |  | 0 | 0 | 0
| 9.04 | [10 empty] | 0 | 0 | 0 | days
[12 empty] | 0 | 0 | 0 | %
|  |  |  | Total Days D10 end of operation B template | 19.65 | 20.38 | 27.06
D(10)
|  |  | Template A | Total Days D10, end of operation A template | 29.69 | 30.75 | 45.32 | 43.38
|  |  | Template B | Total Days D10 end of operation B template | 19.65 | 20.38 | 27.06 | 19.16
|  |  | Template A&B | Total Days D10 end of operation A&B template | 49.33 | 51.13 | 72.37 | 62.53
Note on Q296: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fjernet grenseverdi for vindhastighet etter avklaring fra Morten Rasmussen 20/3

## Sheet1
Subsea support/IMR (Hs= 4,0 m) | Module deployment (Hs= 4,0 m) | Wire Line Intervention (Hs= 6,0 m) | Tubing handling (Hs= 4,0 m) | Umbilical – max disconnect (Hs= 7,0 m)
Klargjøring før iverksettelse av PCE | Installering av PCE | THCP operasjon | Kutting av tubing | WCP tesing/Stack
ROV operations | Uthenting av PCE | Brønnsirkulasjon
As-found undersøkelser |  | Drift run
Åpne WPS / Structure hatches |  | Tubing til annulus-kommunikasjon
Plasser transponders |  | Uthenting av straddles
Pluggeoperasjoner + IPDT
Kamera run